## IT Modernisation
Ref | Programme / project | Category | Owner | Original plan | Revised plan | FY26 spend ($m) | Total budget ($m) | Status
C01 | Data-centre refresh & server fleet | Infrastructure | Raj Malhotra | FY26 | FY26 | 38 | 38 | On plan
C02 | Snowcap data-warehouse expansion | Data platform | Raj Malhotra | FY26 | FY26 | 22 | 30 | On plan
C03 | Authentication platform migration (VPAuth) | Identity & access | Nina Petrov | FY27 | FY26 (accelerated) | 26 | 31 | Accelerated
C04 | Session-signing key rotation & HSM | Identity & access | Nina Petrov | FY27 | FY26 (accelerated) | 14 | 16 | Accelerated
C05 | Backup encryption & retention redesign (legacy_uap) | Data protection | Nina Petrov | FY27 | FY26 (accelerated) | 19 | 22 | Accelerated
C06 | Mobile app re-platform | Product engineering | Maya Hart | FY26 | FY26 | 17 | 24 | On plan
C07 | LumenX exchange capacity upgrade | Advertising platform | Thomas Vale | FY26 | FY26 | 21 | 28 | On plan
C08 | SSOBridge federation hardening | Identity & access | Nina Petrov | FY26 | FY26 | 9 | 12 | On plan
C09 | Network & edge modernisation | Infrastructure | Raj Malhotra | FY26 | FY26 | 16 | 23 | On plan
C10 | Endpoint & device management refresh | IT operations | Raj Malhotra | FY26 | FY26 | 7 | 9 | On plan
C11 | Observability & logging uplift | Reliability | Raj Malhotra | FY26 | FY26 | 11 | 14 | On plan
C12 | Disaster-recovery & resilience programme | Reliability | Raj Malhotra | FY26 | FY26 | 13 | 18 | On plan
Total IT modernisation backlog
IT capital expenditure and modernisation backlog. FY26 spend is the planned capital outlay for the year ending 31 December 2026 ($m).
Several identity-and-access and data-protection projects have been accelerated into FY26 to modernise legacy components and reduce technical debt ahead of decommissioning.