## Vulnerability Register
Vulnerability Register — Q4 2025
VistaPort Media Inc. — Security Engineering — tracked vulnerabilities and remediation status (CONFIDENTIAL)
ID | System | Description | Severity | Status | Due | Owner | Age (days)
VR-2025-0142 | VPAuth | Legacy session-signing key (kid=vpauth-legacy-2019) not rotated since 2019; long-lived signing material on legacy validation path. | Critical | Open — OVERDUE | 30 September 2025 | Nina Petrov | 460
VR-2025-0143 | legacy_uap | legacy_uap backup retained beyond retention policy and protected with weak/legacy encryption; disposition outstanding. | High | Open — OVERDUE | 31 October 2025 | Nina Petrov | 280
VR-2025-0144 | legacy_uap | Stale privileged service accounts retain read access to legacy profile-backup storage; not used in normal operations. | High | Open | 31 December 2025 | Raj Malhotra | 95
VR-2025-0145 | Kestrel Cloud Services | Object-store bucket policy on legacy paths broader than least-privilege; tighten principals. | Medium | In progress | 31 January 2026 | Raj Malhotra | 40
VR-2025-0098 | VistaMail | Outdated TLS cipher suite enabled on a secondary MX endpoint. | Medium | Closed — patched | 15 November 2025 | SecEng | 0
VR-2025-0101 | AtlasID | Verbose error responses on identity-match API leak stack frames. | Low | Closed — patched | 20 November 2025 | SecEng | 0
VR-2025-0110 | LumenX Ad Exchange | Dependency CVE in ad-server image (medium CVSS). | Medium | Closed — patched | 28 November 2025 | SecEng | 0
VR-2025-0112 | SSOBridge | Deprecated SAML connector accepts a weak signature algorithm. | Medium | In progress | 15 January 2026 | SecEng | 30
VR-2025-0118 | Kestrel Cloud Services | Two compute instances missing OS patch baseline. | Medium | Closed — patched | 1 December 2025 | Infra | 0
VR-2025-0121 | Snowcap | Warehouse role grants exceed least-privilege for two analyst roles. | Low | In progress | 20 January 2026 | Data Platform | 25
VR-2025-0125 | VPAuth | Session cookie missing one hardening attribute on a legacy path. | Medium | In progress | 10 January 2026 | Nina Petrov | 35
VR-2025-0129 | VistaMail | Rate-limiting gap on password-reset endpoint. | Medium | Closed — patched | 5 December 2025 | SecEng | 0
VR-2025-0131 | Corporate IT | Three laptops with outdated EDR agent version. | Low | Closed — remediated | 22 November 2025 | IT Ops | 0
VR-2025-0133 | AtlasID | Logging gap on a deprecated match endpoint. | Low | Closed — patched | 8 December 2025 | SecEng | 0
VR-2025-0136 | Kestrel Cloud Services | Egress monitoring threshold tuned too high on one storage account; lowered after review. | Medium | Closed — tuned | 12 December 2025 | SOC | 0
VR-2025-0138 | Corporate IT | Phishing-resistant MFA not yet enforced for one admin group. | Medium | In progress | 1 February 2026 | IT Ops | 20
VR-2025-0140 | VPAuth | Key-rotation automation not implemented for legacy key set. | High | Open | 31 December 2025 | Nina Petrov | 95
VR-2025-0146 | legacy_uap | Decommission of legacy profile store behind roadmap schedule. | Medium | In progress | 31 March 2026 | Raj Malhotra | 0
VR-2025-0148 | SSOBridge | Stale OAuth client credentials for a retired internal tool. | Low | Closed — revoked | 18 December 2025 | SecEng | 0
VR-2025-0150 | Snowcap | Service account with broad export grant; scope reduced. | Medium | Closed — reduced | 20 December 2025 | Data Platform | 0
VR-2025-0152 | Corporate IT | Outdated VPN client on legacy contractor laptops. | Low | In progress | 25 January 2026 | IT Ops | 18
VR-2025-0154 | LumenX Ad Exchange | Verbose debug header in non-prod leaked to staging. | Informational | Closed | 2 December 2025 | SecEng | 0
Severity per CVSS-aligned internal scale. 'OVERDUE' = past due date and unremediated.
Items VR-2025-0142 and VR-2025-0143 relate to legacy authentication/backup components in active decommission and carry standing risk-acceptance pending the FY2026 roadmap.